## Testing Log
Date | Description of Test | Passed (Y/N) | GitHub Issue Nbr | Notes
2020-09-20 | Testing number display when pressing number pad | Y |  | All numbers from 0 - 9 display on the input field
2020-09-20 | Displaying operations | Y |  | All operations display on the input field
2020-09-20 | Clearing input when pressing the "C" button | Y |  | All input deletes when pressing "C"
2020-09-23 | Adding two values | Y |  | Took two values and summed them using +
2020-09-23 | Subtracting two values | Y |  | Received desired result
2020-09-23 | Dividing two values | Y |  | Received desired result
2020-09-23 | Multiplying two values | Y |  | Received desired result
2020-09-23 | Power of two values | Y |  | Received desired result
2020-09-23 | Creating algebraic equations | Y |  | Can get results of more than one operation and value
2020-09-23 | Using keyboard "Enter" to received result | N | #1 | Summed values using keyboard, no results.
2020-09-23 | Entering values and operations manually on screen | Y |  | Typed numbers, used calculators =, got result
2020-09-23 | Operation first and then values (Sum, Subtract) | Y |  | The calculator reads the add and subtract as value signs.
2020-09-23 | Operation first and then values (Multiply, Divide, Power) | N | #2 | Operations return error message on console log.
2020-09-23 | Only clicking equals button | N | #3 | Only clicking "equals" returns "undefined" on screen.
2020-09-23 | Operations only test | N | #4 | Only clicking operations and then clicking equals shows error.
2020-09-23 | Division by zero tests | Y |  | Dividing a value by zero displays "infinity" on the screen.
2020-09-23 | Typing letters on the input field test | N | #5 | Typing letters on the input field shows an error on the console log.
2020-09-23 | Creating a textarea on the inputfield | Y |  | When submitting a textarea on the inputfield, no textarea appears. May need to run more tests.
2020-09-23 | Only clicking equals button
2020-09-23 | Spamming numbers on the input field | Y |  | No errors appeared. Just remained waiting for operations.
2020-09-23 | Double negative sign on value | N | #6 | Attempting to add a double negative sign before a value returns an error.
2020-09-23 | Adding an extremely large number | Y |  | The large value returned a very large result. May need to run more tests.
2020-09-23 | Entering a period in between values | Y |  | Entering a period in between numbers and calculating them with an operation works fine.
2020-09-23 | Diving zero with zero | Y |  | Result returns NaN
2020-09-23 | Spamming similar operations | N | #7 | Receive error on console log.
2020-09-23 | Attempting an HTML/PHP Injection on the input field | N | #8 | Error message appeared, need to try more tests.
2020-09-23 | Image linking on input field | N | #9 | Error on console log showing unexpected characters.
2020-09-23 | Diving a result with a multiplier before it | N | #10 | Error on console log showing unexpected characters.
2020-09-23 | Removing HTML classes | Y |  | Removed HTML classes important to JS file and had not any errors appear on the console log.
2020-09-23 | Disabling JavaScript on debugger | Y |  | Buttons were disabled, no functionality occurred but no errors either.
2020-09-23 | Removing C buttons ID and class | Y | #11 | Cleared C buttons identifiers, still worked. Need to see what it is.
2020-09-25 | Mobile resizing issues | N | #12 | Issues resizing calculator to mobile size
API and Security Tests
2020-10-26 | Can't connect Swagger API to Calculator page | Y | #15 | Wasn't able to see requests. Fixed paths.
2020-10-26 | 404 error message on Swagger | Y | #16 | Parameter issues and also worked on the logic in root folder
2020-10-26 | Can only see GET method | Y | #17
2020-10-27 | Issues attempting to save POST result | N | #18 | Tried storing POST request in a variable. No cookies involved yet.
2020-10-27 | POST displays as an array | N | #19 | Had not created cookies yet.
2020-10-27 | Issues with oAuth security URL redirect | Y | #20 | oAuth now verifies authentication for requests.
2020-10-27 | Need security tests for oAuth and OpenAPI | Y | #21 | Can see all security measurments working properly though more tests are needed
2020-10-27 | Cant receive PUT, DELETE and HEAD requests | N | #22 | Unsure what the output should be like. No parameters are being used.
Note on D1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Required, if Passed is "N"